## April 1
|  |  | Weekly Sprint Sheet |  | Team Members | Email
Project: Multi-Plyer, Network Game |  |  |  |  | krunal chaudhari | kchaud6
Week Of: 4/19/2019 |  |  |  |  | pranav patel | ppate379
[5 empty] | kevin patel | kpate322
[5 empty] | yash patel | ypatel43
Action Item | Item ID | Team Member | Last Week | This Week | Next Week | Issues
UML-Game structure | 1 | yash patel | N/A | Draw UML and plan out game structure on paper. Ex. Classes needed as of now. | further progress the project with pranav
implement with basic starting game without any rules | 2 | krunal chaudhari | N/A | Working on serverside and connection client for basic gui and card delt | further progress the project with pranav
implement with basic starting game with rules from where krunal leaves | 3 | pranav patel | N/A | pick it up from where krunal leaves and implement rules | further progress the project with pranav
basic server and client connection | 4 | kevin patel | N/A | start the server and connect client with simple gui. | further progress the project with pranav